## Updated
S.No. | State | Total No. of Districts | No. of Districts Targeted for Rabi DCS | Total No. of Villages | No. of Villages Geo-referenced | % Villages geo-referenced | No. of Villages Targeted for Rabi DCS | % Villages targeted for Rabi DCS | Total No. of Plots | No. of Plots Geo-referenced | % Plots geo-refenced | No. of Plots Targeted for Rabi DCS | % Plots targeted for Rabi DCS | Total Districts where DCS has started | Total Villages where DCS started | Total Plots Surveyed- 15.12.2025 | Total Plots Surveyed- 16.12.2025 | Total Plots Surveyed- 18.12.2025 | Total Plots Surveyed- 19.12.2025 | Total Plots Surveyed- 22.12.2025 | Total Plots Surveyed- 23.12.2025 | Total Plots Surveyed- 24.12.2025 | Total Plots Surveyed- 25.12.2025 | Total Plots Surveyed- 26.12.2025 | Total Plots Surveyed- 27.12.2025 | Total Plots Surveyed- 28.12.2025 | Total Plots Surveyed- 29.12.2025 | Total Plots Surveyed- 30.12.2025 | Total Plots Surveyed- 31.12.2025 | Total Plots Surveyed- 01.01.2026 | Total Plots Surveyed- 02.01.2026 | Total Plots Survyed- 03.01.2026 | Total Plots Surveyed - 04.01.2026 | Total Plots Surveyed - 05.01.2026 | Total Plots Surveyed - 06.01.2026 | Total Plots Surveyed - 07.01.2026 | Total Plots Surveyed - 08.01.2026 | Total Plots Surveyed - 09.01.2026 | Total Plots Surveyed - 10.01.2026 | Total Plots Surveyed - 11.01.2026 | Total Plots Surveyed - 12.01.2026 | Total Plots Surveyed - 13.01.2026 | DCS Completion %age(Plot Level) | Rabi DCS Activity Start Date | Rabi DCS Activity End Date | Top 5 Rabi Crops Sown in the State | Total Surveyors to Be Deployed | Master Trainers Training – Conducted (Yes/No). If No, Proposed Date | Surveyors Training – Conducted (Yes/No). If No, Proposed Date
1 | Tamil Nadu | 38 | 37 | 17164 | 17164 | 100% | 17116 | 99.72% | 46811114 | 42543798 | 90.88% | 42543798 | 90.88% | 37 | 16298 | 1026364 | 1069452 | 1311768 | 1454146 | 1834770 | 2053663 | 2296116 | 2712234 | 2987676 | 3458945 | 3811979 | 3970297 | 4492300 | 5039095 | 5601452 | 5731067 | 6381389 | 6655559 | 6871606 | 7266342 | 7750745 | 8363147 | 9120971 | 10900955 | 10900955 | 10900955 | 11617964 | 24.82% | 01.12.2025 | 15.01.2026 | Rice, Maize, Blackgram, Jowar, Groundnut | 17116 | Yes | Yes
2 | Maharashtra | 34 | 34 | 44295 | 44219 | 99.83% | 25391 |  | 32148760 | 14078965 | 43.79% | 32148760 |  | 34 | 25391 |  | 35517 | 73992 | 89819 | 183866 | 206649 | 219626 | 219626 | 219626 | 287929 | 323087 | 347545 | 374509 | 420644 | 444045 | 469737 | 495210 | 495210 | 521013 | 543008 | 570235 | 591176 | 613029 | 634804 | 634804 | 683360 | 792082 | 2.464% | 10.12.2025 | 10.03.2026 | Gram, Wheat, Onion,Jowar,Maize | 64340 | Yes | Yes
3 | Andhra Pradesh | 26 | 26 | 17558 | 13147 | 74.88% | 14296 | 81.42% | 13191602 | 11559292 | 87.63% | 13191602 | 100% | 26 | 14327 |  |  | 822 | 6499 | 14276 | 45181 | 75229 | 75229 | 104753 | 104753 | 138292 | 178123 | 232382 | 288574 | 288574 | 319441 | 319441 | 319441 | 319441 | 319441 | 589603 | 684663 | 794465 | 794465 | 794465 | 928512 | 1027949 | 7.792% | 17.12.2025 | 28.02.2026 | Paddy, Bengalgram, Blackgram, Maize, Groundnut | 9000 | Yes | Yes
4 | Kerala | 14 | 14 | 1666 | 801 | 48.08% | 600 | 36.01% | 31442791 | 15117273 | 48.08% | 9800000 | 31.17% | 14 | 573 |  |  | 161814 | 262221 | 635723 | 794667 | 969157 | 1139018 | 1253539 | 1409507 | 1596307 | 1706137 | 1879590 | 2073707 | 2257197 | 2388617 | 2582843 | 2726872 | 2852216 | 3024795 | 3205065 | 3379544 | 3552472 | 3726886 | 3809886 | 4009339 | 4282228 | 13.62% | 15.12.2025 | 28.02.2026 | Rice, Vegetables, Banana, Legumes, Tubers | 9000 | Yes | Yes
5 | Jharkhand | 24 | 24 | 32739 | 32739 | 100% | 32739 | 100% | 28278388 | 28278388 | 100% | 28278388 | 100% | 24 | 6701 |  | 116 | 971 | 3669 | 23205 | 33196 | 46383 | 71046 | 101394 | 123150 | 159954 | 211780 | 246929 | 296978 | 348057 | 395126 | 470312 | 539876 | 667615 | 763602 | 876504 | 1007106 | 1147617 | 1278360 | 1538176 | 1698278 | 2002770 | 7.082% | 16.12.2025 | 30.01.2026 | Wheat, Gram (Chana), Lentil (Masoor), Pea (Matar), Mustard | 50,000 approx | Yes | No, 8th to 13th Dec
6 | Odisha | 30 | 30 | 51542 | 49423 | 95.89% | 49423 | 95.89% | 29502369 | 29502369 | 100% | 29502369 | 100% | 30 | 10396 |  |  |  |  | 31159 | 46907 | 80126 | 148530 | 203887 | 268031 | 344710 | 420211 | 498357 | 589012 | 678383 | 759936 | 884684 | 1046180 | 1232668 | 1438894 | 1685022 | 1992366 | 2300438 |  | 2847468 | 3257877 | 3652875 | 12.38% | 16.12.2025 | 28.02.2026 | Paddy, Greengram, Blackgram, Groundnut, Horsegram | 30000 | No, 10-15th Dec 2025 | No, 10-15th Dec 2025
7 | Gujarat | 34 | 34 | 18464 | 18464 | 100% | 18464 | 100% | 9500000 | 9500000 | 100% | 9500000 | 100% | 34 | 15623 |  |  | 154155 | 283489 | 787172 | 947027 | 1134711 | 1330551 | 1544425 | 1743183 | 1989223 | 2181933 | 2366833 | 2561832 | 2760893 | 2994370 | 3204188 | 3439656 | 3699789 | 3922732 | 4180591 | 4425692 | 4659733 | 4880897 | 5129756 | 5350874 | 5583542 | 58.77% | 16.12.2025 | 31.01.2026 | Wheat, Chickpea, Cumin, Mustard, Maize | 20000 | No, Planning for 3rd Dec | No, Planning for 5th Dec by Master Trainers
8 | Himachal Pradesh | 12 | 11 | 21592 | 18614 | 86.21% | 5400 | 25.01% | 13920370 | 11919995 | 85.63% | 2500000 | 17.96% | 12 | 291 |  |  |  |  | 1118 | 1566 | 2459 | 3345 | 3806 | 4332 | 5016 | 5731 | 6412 | 16058 | 8813 | 9674 | 10673 | 11157 | 13982 | 16058 | 18810 | 21715 | 25564 | 30499 | 36653 | 43443 | 50837 | 0.3652% | 17.12.2025 | 15.03.2026 | Wheat, Potato, Pea, Mustard, Garlic, Cole Crop, Horticulture Crops (Citrus) | At least 1 per Panchayat (Approx 3500 Panchayat) | Yes | No, 15-12-25 to 20-12-25
9 | Bihar | 38 | 38 | 45536 | 38513 | 84.58% | 30416 | 66.8% | 40000000 | 19400000 | 48.5% | 19400000 | 48.5% | 34 | 2234 | [12 empty] | 21 | 478 | 2371 | 5476 | 16502 | 30827 | 49530 | 73730 | 101512 | 122665 | 139817 | 157275 | 175512 | 191881 | 220206 | 0.5505% | 28.12.2025 | 31.03.2026 | Wheat, Lentil, Chickpea, Maize, Indian Mustard | 9211 | Yes | No, Proposed by 3rd week of Dec
10 | Telangana | 32 | 32 | 10621 | 9795 | 92.22% | 9795 | 92.22% | 19469000 | 17436000 | 89.56% | 17436000 | 89.56% | [29 empty] | 0% | 01.01.2026 | 10.01.2026 | Paddy, Maize, Jowar, Groundnut, Bengalgram | 6975 | Yes | No
11 | Mizoram | 11 | 11 | 864 | 277 | 32.06% | 150 | 17.36% | 45000 | 13000 | 28.89% | 5000 | 11.11% | [29 empty] | 0% | 01.01.2025 | 28.02.2026 | Pea, Cabbage, Mustard, Tomato, Bean | 50 | Yes | Yes
12 | Uttar Pradesh | 75 | 75 | 110236 | 95765 | 86.87% | 92686 | 84.08% | 76277576 | 54594234 | 71.57% | 61145571 | 80.16% | 75 | 46189 | [19 empty] | 212474 | 758015 | 1864774 | 2586190 | 3457238 | 5107059 | 6781700 | 8033989 | 10.53% | 01.01.2026 | 15.02.2026 | Wheat, Mustard, Potato, Pea, Chana, Masoor | Not Confirmed | No, Proposed in 3rd week of Dec | No, Proposed in 3rd week of Dec
13 | Rajasthan | 41 | 41 | 48909 | 48797 | 99.77% | 48797 | 99.77% | 45459806 | 45238362 | 99.51% | 28051487 | 61.71% | 41 | 7818 | [18 empty] | 320000 | 380000 | 430000 | 330070 | 44079 | 65964 | 93741 | 125653 | 167660 | 0.3688% | 01.01.2026 | 05.03.2026 | Wheat, Mustard, Chickpea (Gram), Barley, Cumin | 7,870 Pvt Surveyor + 7,714 Govt Patwari | Proposed on 15.12.2025 | Proposed on 24.12.2025
14 | Chhattisgarh | 33 | 33 | 20551 | 18959 | 92.25% | 18959 | 92.25% | 25227439 | 18894295 | 74.9% | 18894295 | 74.9% | 25 | 980 | [15 empty] | 2 | 2761 | 13405 | 37943 | 65787 | 104456 | 155503 | 200471 | 245576 | 298251 | 338111 | 427739 | 1.696% | 01.01.2026 (Approval pending at Administrative Level) | 15,02.2026 (Approval Pending at Administrative Level) | चना,गहू, तबरा/लाख,राई/सरसो,अलसी | 40000 | Yes, on 27.11.2025 | Master Training conducted, Surveyors training will be conducted by Master Trainers in District
15 | Uttarakhand | 13 | 13 | 16691 | 16689 | 99.99% | 6300 | 37.74% | 28383886 | 28383886 | 100% | 10713467 | 37.74% | 7 | 79 | [18 empty] | 44 | 167 | 256 | 536 | 1051 | 1853 | 2104 | 2358 | 2987 | 0.01052% | In Plain districts- 1st January 2026 In Hilly districts- 15th January 2026 | In Plain districts- 15th February 2026 In Hilly districts- 15th May 2026 | Wheat, Barley, Lentil (Masoor), Mustard, Pea | 2300 | Yes | No, in Dec 2nd week
16 | Tripura | 8 | 8 | 897 | 897 | 100% | 450 | 50.17% | 2200000 | 2200000 | 100% | 800000 | 36.36% | [29 empty] | 0% | 15.01.2025 | 15.02.2026 | Rice, Oil Seed, Pulse, Maize, Potato | 820 | Yes | Yes
17 | Assam | 35 | 30 | 18407 | 16237 | 88.21% | 12983 | 70.53% | 3909970 | 3909970 | 100% | 3909970 | 100% | 29 | 2691 | [18 empty] | 1099 | 9506 | 42296 | 94599 | 159270 | 228142 | 303992 | 370349 | 419775 | 10.74% | 05.01.2026 | 20.02.2026 | Rape & Mustard, Maize, Summer Paddy, Black Gram, Rabi Vegetables | 15453 | No, 19.12.2025 | No. Training shall be conducted by Mastrer Trainer before 31st Dec 2025
18 | Madhya Pradesh | 55 | 55 | 56109 | 55431 | 98.79% | 55431 | 98.79% | 47875774 | 47875774 | 100% | 47875774 | 100% | [29 empty] | 0% | 21.01.2026 | 28.02.2026 |  | 85000 | No,20.01.2026 | No,20.01.2026
19 | Andaman & Nicobar | 3 | 3 | 204 | 177 | 86.76% | 177 | 86.76% | 31527 | 25410 | 80.6% | 25410 | 80.6% | [29 empty] | 0% | 01.02.2026 | 18.03.2026 | 1. Solanaceous crops(Chilli, Brinjal, Tomato etc.) 2. Cucurbitaceous crops(Cucumber,Bottle gourd, Pumpkin, Water Melon etc.) 3. Cole crops(Cabbage, Cauliflower, Knolkhol etc.) 4. Malvaceae crops(Okra) 5. Leafy Vegetable(Spinach, Amaranthus, Poi etc.) | 177 | Yes | No, to be conducted in the 2nd week of Dec
20 | Haryana | 22 | 22 | 7103 | 2753 | 38.76% | 2753 | 38.76% | 17846314 | 5487977 | 30.75% | 5487977 | 30.75% | [29 empty] | 0% | 01.02.2026 | 15.03.2026 | Wheat, Mustard, Gram, Barley, Potato | 5000 | Yes | No, Proposed date 17.12.2025
21 | Jammu & Kashmir | 20 | 20 | 6857 | 6014 | 87.71% | 1731 | 25.24% | 6000000 | 5520000 | 92% | 925732 | 15.43% | [29 empty] | 0% | 15.02.2026 | 15.04.2026 | Oilseed, Wheat, Oats, Vegetables, Field pea | 5000 | Yes | No, Proposed Date 05.01.2026
22 | Punjab | 23 | 23 | 13004 | 9371 | 72.06% | 9371 | 72.06% | 20802747 | 13102354 | 62.98% | To be finalized | [30 empty] | 0% | 15.02.2026 (tentative) | 15.04.2026 (tentative) | Wheat, Gram, Barley, Rabi Oil Seeds, Lentil | To be finalized | No, 1st week of Feb (tentative) | No, 1st week of Feb (tentative)
23 | Karnataka | [41 empty] | #DIV/0!
24 | Sikkim | [41 empty] | #DIV/0!
25 | Goa | [41 empty] | #DIV/0!
26 | Arunachal Pradesh | [41 empty] | #DIV/0!
27 | Manipur | [41 empty] | #DIV/0!
| Total | 621 | 614 | 561009 | 514246 |  | 453428 |  | 538324433 | 424581342 | 17.3527 | 382135600 |  | 422 | 149591 | 1026364 | 1105085 |  | 2099843 | 3511289 | 4128856 | 4823807 | 5699579 | 6419106 | 7399830 | 8368568 | 9021757 | 10097333 | 11286378 | 12389785 | 13073446 |  | 15278183 | 16586946 | 18036536 | 20313110 | 23033556 | 25345167 | 26402914 | 31672822 | 34682690 | 38282603
S

## Sheet2
State | No. of Plots Targeted for Rabi DCS | Total Plots Surveyed - 12.01.2026 | Rabi DCS Activity Start Date | Rabi DCS Activity End Date | days | Total Days | Days Elapsed | Required /day | Actual /day | Required % (Time elapsed) | Actual % (Survey done) | Gap
Tamil Nadu | 42543798 | 10900955 | 01.12.2025 | 15.01.2026 | 45 | 45 | 43 | 945418 | 253510 | 95.6% | 25.6% | 🔻-70.0%
Maharashtra | 32148760 | 683360 | 10.12.2025 | 10.03.2026 | 90 | 90 | 34 | 357208 | 20099 | 37.8% | 2.1% | 🔻-35.7%
Andhra Pradesh | 13191602 | 928512 | 17.12.2025 | 28.02.2026 | 73 | 73 | 27 | 180707 | 34389 | 37% | 7% | 🔻-30.0%
Kerala | 9800000 | 4009339 | 15.12.2025 | 28.02.2026 | 75 | 75 | 29 | 130667 | 138253 | 38.7% | 40.9% | ✅ +2.2%
Jharkhand | 28278388 | 1698278 | 16.12.2025 | 30.01.2026 | 45 | 45 | 28 | 628409 | 60653 | 62.2% | 6% | 🔻-56.2%
Odisha | 29502369 | 3257877 | 16.12.2025 | 28.02.2026 | 74 | 74 | 28 | 398680 | 116353 | 37.8% | 11% | 🔻-26.8%
Gujarat | 9500000 | 5350874 | 16.12.2025 | 31.01.2026 | 46 | 46 | 28 | 206522 | 191103 | 60.9% | 56.3% | 🔻-4.6% (near track)
Himachal Pradesh | 2500000 | 43443 | 17.12.2025 | 15.03.2026 | 88 | 88 | 27 | 28409 | 1609 | 30.7% | 1.7% | 🔻-29.0%
Bihar | 19400000 | 191881 | 28.12.2025 | 31.03.2026 | 93 | 93 | 16 | 208602 | 11993 | 17.2% | 1% | 🔻-16.2%
Uttar Pradesh | 61145571 | 6781700 | 01.01.2026 | 15.02.2026 | 45 | 45 | 12 | 1358791 | 565142 | 26.7% | 11.1% | 🔻-15.6%
Rajasthan | 28051487 | 125653 | 01.01.2026 | 05.03.2026 | 63 | 63 | 12 | 445262 | 10471 | 19% | 0.4% | 🔻-18.6%
Chhattisgarh | 18894295 | 338111 | 01.01.2026 (Approval pending at Administrative Level) | 15,02.2026 (Approval Pending at Administrative Level) | 45 | 45 | 12 | 1259620 | 28176 | 80% | 1.8% | 🔻-78.2%
Assam | 3909970 | 370349 | 05.01.2026 | 20.02.2026 |  | 46 | 8 | 85216 | 46294 | 17.4% | 9.5% | 🔻-7.9%
Madhya Pradesh | 47875774 |  | 21.01.2026 | 28.02.2026
Andaman & Nicobar | 25410 |  | 01.02.2026 | 18.03.2026
Haryana | 5487977 |  | 01.02.2026 | 15.03.2026
Jammu & Kashmir | 925732 |  | 15.02.2026 | 15.04.2026
Punjab | To be finalized |  | 15.02.2026 (tentative) | 15.04.2026 (tentative)
Karnataka
Sikkim
Goa
Arunachal Pradesh
Manipur
Total | 353181133 | 34680332

## Sheet1
S.No. | State | Total No. of Districts | No. of Districts Targeted for Rabi DCS | Total No. of Villages | No. of Villages Geo-referenced | % Villages geo-referenced | No. of Villages Targeted for Rabi DCS | % Villages targeted for Rabi DCS | Total No. of Plots | No. of Plots Geo-referenced | % Plots geo-refenced | No. of Plots Targeted for Rabi DCS | % Plots targeted for Rabi DCS | Rabi DCS Activity Start Date | Rabi DCS Activity End Date | Top 5 Rabi Crops Sown in the State | Total Surveyors to Be Deployed | Master Trainers Training – Conducted (Yes/No). If No, Proposed Date | Surveyors Training – Conducted (Yes/No). If No, Proposed Date
1 | Tamil Nadu | 38 | 37 | 17164 | 17164 | 100% | 17116 | 99.72% | 46811114 | 42300095 | 90.36% | 42300095 | 90.36% | 01.12.2025 | 15.01.2026 | Rice, Maize, Blackgram, Jowar, Groundnut | 17116 | Yes | Yes
2 | Andhra Pradesh | 26 | 26 | 17558 | 13147 | 74.88% | 14296 | 81.42% | 13191602 | 11559292 | 87.63% | 13191602 | 100% | 11.12.2025 | 28.02.2026 | Paddy, Bengalgram, Blackgram, Maize, Groundnut | 9000 | Yes | Yes
3 | Kerala | 14 |  | 1666 | 801 | 48.08% | 600 | 36.01% | 31442791 | 15117273 | 48.08% | 9800000 | 31.17% | 15.12.2025 | 28.02.2026 | Rice, Vegetables, Banana, Legumes, Tubers | 9000 | Yes | Yes
4 | Gujarat | 34 | 34 | 18464 | 18464 | 100% | 18464 | 100% | 9500000 | 9500000 | 100% | 9500000 | 100% | 16.12.2025 | 31.01.2026 | Wheat, Chickpea, Cumin, Mustard, Maize | 20000 | No, Planning for 3rd Dec | No, Planning for 5th Dec by Master Trainers
5 | Jharkhand | 24 | 24 | 32739 | 32739 | 100% | 32739 | 100% | 28278388 | 28278388 | 100% | 28278388 | 100% | 15.12.2025 | 30.01.2026 | Wheat, Gram (Chana), Lentil (Masoor), Pea (Matar), Mustard | 50,000 approx | Yes | No, 8th to 13th Dec
6 | Odisha | 30 | 30 | 51542 | 49423 | 95.89% | 49423 | 95.89% | 29502369 | 29502369 | 100% | 29502369 | 100% | 15.12.2025 | 28.02.2026 | Paddy, Greengram, Blackgram, Groundnut, Horsegram | 30000 | No, 10-15th Dec 2025 | No, 10-15th Dec 2025
7 | Telangana | 32 | 32 | 10621 | 9795 | 92.22% | 9795 | 92.22% | 19469000 | 17436000 | 89.56% | 17436000 | 89.56% | 20.12.2025 | 10.01.2026 | Paddy, Maize, Jowar, Groundnut, Bengalgram | 6975 | Yes | No
8 | Himachal Pradesh | 12 | 11 | 21592 | 18614 | 86.21% | 5400 | 25.01% | 13920370 | 11919995 | 85.63% | 2500000 | 17.96% | 25.12.2025 | 15.03.2026 | Wheat, Potato, Pea, Mustard, Garlic, Cole Crop, Horticulture Crops (Citrus) | At least 1 per Panchayat (Approx 3500 Panchayat) | Yes | No, 15-12-25 to 20-12-25
9 | Tripura | 8 | 8 | 897 | 897 | 100% | 450 | 50.17% | 2200000 | 2200000 | 100% | 800000 | 36.36% | 15.12.2025 | 15.02.2026 | Rice, Oil Seed, Pulse, Maize, Potato | 820 | Yes | Yes
10 | Mizoram | 11 | 11 | 864 | 277 | 32.06% | 150 | 17.36% | 45000 | 13000 | 28.89% | 5000 | 11.11% | 15.12.2025 | 28.02.2026 | Pea, Cabbage, Mustard, Tomato, Bean | 50 | Yes | Yes
11 | Chhattisgarh | 33 | 33 | 20551 | 18959 | 92.25% | 18959 | 92.25% | 25227439 | 18894295 | 74.9% | 18894295 | 74.9% | 01.01.2026 (Approval pending at Administrative Level) | 15,02.2026 (Approval Pending at Administrative Level) | चना,गहू, तबरा/लाख,राई/सरसो,अलसी | 40000 | Yes, on 27.11.2025 | Master Training conducted, Surveyors training will be conducted by Master Trainers in District
12 | Uttar Pradesh | 75 | 75 | 110236 | 95765 | 86.87% | Not Confirmed | #VALUE! | 76277576 | 54594234 | 71.57% | Not Confirmed | #VALUE! | 01.01.2026 | 15.02.2026 | Wheat, Mustard, Potato, Pea, Chana, Masoor | Not Confirmed | No, Proposed in 3rd week of Dec | No, Proposed in 3rd week of Dec
13 | Uttarakhand | 13 | 13 | 16691 | 16689 | 99.99% | 6300 | 37.74% | 28383886 | 28383886 | 100% | 10713467 | 37.74% | In Plain districts- 1st January 2026 In Hilly districts- 15th January 2026 | In Plain districts- 15th February 2026 In Hilly districts- 15th May 2026 | Wheat, Barley, Lentil (Masoor), Mustard, Pea | 2300 | Yes | No, in Dec 2nd week
14 | Rajasthan | 41 | 41 | 48909 | 48797 | 99.77% | 48797 | 99.77% | 45459806 | 45238362 | 99.51% | 28051487 | 61.71% | 01.01.2026 | 05.03.2026 | Wheat, Mustard, Chickpea (Gram), Barley, Cumin | 7,870 Pvt Surveyor + 7,714 Govt Patwari | Proposed on 15.12.2025 | Proposed on 24.12.2025
15 | Assam | 35 | 30 | 18407 | 16237 | 88.21% | 12983 | 70.53% | 3909970 | 3909970 | 100% | 3909970 | 100% | 05.01.2026 | 20.02.2026 | Rape & Mustard, Maize, Summer Paddy, Black Gram, Rabi Vegetables | 15453 | No, 19.12.2025 | No. Training shall be conducted by Mastrer Trainer before 31st Dec 2025
16 | Bihar | 38 | 38 | 45536 | 38513 | 84.58% | 30416 | 66.8% | 40000000 | 19400000 | 48.5% | 19400000 | 48.5% | Phase-wise Tentative 24 Dec and later | 31.03.2026 | Wheat, Lentil, Chickpea, Maize, Indian Mustard | 9211 | Yes | No, Proposed by 3rd week of Dec
17 | Madhya Pradesh | 55 | 55 | 56109 | 55431 | 98.79% | 55431 | 98.79% | 47875774 | 47875774 | 100% | 47875774 | 100% | 21.01.2026 | 28.02.2026 |  | 85000 | No,20.01.2026 | No,20.01.2026
18 | Haryana | 22 | 22 | 7103 | 2753 | 38.76% | 2753 | 38.76% | 17846314 | 5487977 | 30.75% | 5487977 | 30.75% | 01.02.2026 | 15.03.2026 | Wheat, Mustard, Gram, Barley, Potato | 5000 | Yes | No, Proposed date 17.12.2025
19 | Andaman & Nicobar | 3 | 3 | 204 | 177 | 86.76% | 177 | 86.76% | 31527 | 25410 | 80.6% | 25410 | 80.6% | 01.02.2026 | 18.03.2026 | 1. Solanaceous crops(Chilli, Brinjal, Tomato etc.) 2. Cucurbitaceous crops(Cucumber,Bottle gourd, Pumpkin, Water Melon etc.) 3. Cole crops(Cabbage, Cauliflower, Knolkhol etc.) 4. Malvaceae crops(Okra) 5. Leafy Vegetable(Spinach, Amaranthus, Poi etc.) | 177 | Yes | No, to be conducted in the 2nd week of Dec
20 | Punjab | 23 | 23 | 13004 | 9371 | 72.06% | 9371 | 72.06% | 22302747 | 13102354 | 58.75% | To be finalized |  | 15.02.2026 (tentative) | 15.04.2026 (tentative) | Wheat, Gram, Barley, Rabi Oil Seeds, Lentil | To be finalized | No, 1st week of Feb (tentative) | No, 1st week of Feb (tentative)
21 | Jammu & Kashmir | 20 | 20 | 6857 | 6014 | 87.71% | 1731 | 25.24% | 6000000 | 5520000 | 92% | 925732 | 15.43% | 15.02.2026 | 15.04.2026 | Oilseed, Wheat, Oats, Vegetables, Field pea | 5000 | Yes | No, Proposed Date 05.01.2026
22 | Goa
23 | Sikkim
24 | Manipur
25 | Arunachal Pradesh
26 | Maharashtra
27 | Karnataka