## Sheet 1
Table 1
S.No. | State | Total No. of Districts | No. of Districts Targeted for Rabi DCS | Total No. of Villages | No. of Villages Geo-referenced | % Villages geo-referenced | No. of Villages Targeted for Rabi DCS | % Villages targeted for Rabi DCS | Total No. of Plots | No. of Plots Geo-referenced | % Plots geo-refenced | No. of Plots Targeted for Rabi DCS | % Plots targeted for Rabi DCS | Rabi DCS Activity Start Date | Rabi DCS Activity End Date | Top 5 Rabi Crops Sown in the State | Total Surveyors to Be Deployed | Master Trainers Training – Conducted (Yes/No). If No, Proposed Date | Surveyors Training – Conducted (Yes/No). If No, Proposed Date
1 | Tamil Nadu | 38 | 37 | 17164 | 17164 | 100% | 17116 | 99.72% | 46811114 | 42300095 | 90.36% | 42300095 | 90.36% | 01.12.2025 | 15.01.2026 | Rice, Maize, Blackgram, Jowar, Groundnut | 17116 | Yes | Yes
2 | Andhra Pradesh | 26 | 26 | 17558 | 13147 | 74.88% | 14296 | 81.42% | 13191602 | 11559292 | 87.63% | 13191602 | 100% | 11.12.2025 | 28.02.2026 | Paddy, Bengalgram, Blackgram, Maize, Groundnut | 9000 | Yes | Yes
3 | Kerala | 14 |  | 1666 | 801 | 48.08% | 600 | 36.01% | 31442791 | 15117273 | 48.08% | 9800000 | 31.17% | 15.12.2025 | 28.02.2026 | Rice, Vegetables, Banana, Legumes, Tubers | 9000 | Yes | Yes
4 | Gujarat | 34 | 34 | 18464 | 18464 | 100% | 18464 | 100% | 9500000 | 9500000 | 100% | 9500000 | 100% | 16.12.2025 | 31.01.2026 | Wheat, Chickpea, Cumin, Mustard, Maize | 20000 | No, Planning for 3rd Dec | No, Planning for 5th Dec by Master Trainers
5 | Jharkhand | 24 | 24 | 32739 | 32739 | 100% | 32739 | 100% | 28278388 | 28278388 | 100% | 28278388 | 100% | 15.12.2025 | 30.01.2026 | Wheat, Gram (Chana), Lentil (Masoor), Pea (Matar), Mustard | 50,000 approx | Yes | No, 8th to 13th Dec
6 | Odisha | 30 | 30 | 51542 | 49423 | 95.89% | 49423 | 95.89% | 29502369 | 29502369 | 100% | 29502369 | 100% | 15.12.2025 | 28.02.2026 | Paddy, Greengram, Blackgram, Groundnut, Horsegram | 30000 | No, 10-15th Dec 2025 | No, 10-15th Dec 2025
7 | Telangana | 32 | 32 | 10621 | 9795 | 92.22% | 9795 | 92.22% | 19469000 | 17436000 | 89.56% | 17436000 | 89.56% | 20.12.2025 | 10.01.2026 | Paddy, Maize, Jowar, Groundnut, Bengalgram | 6975 | Yes | No
8 | Himachal Pradesh | 12 | 11 | 21592 | 18614 | 86.21% | 5400 | 25.01% | 13920370 | 11919995 | 85.63% | 2500000 | 17.96% | 25.12.2025 | 15.03.2026 | Wheat, Potato, Pea, Mustard, Garlic, Cole Crop, Horticulture Crops (Citrus) | At least 1 per Panchayat (Approx 3500 Panchayat) | Yes | No, 15-12-25 to 20-12-25
9 | Tripura | 8 | 8 | 897 | 897 | 100% | 450 | 50.17% | 2200000 | 2200000 | 100% | 800000 | 36.36% | 15.12.2025 | 15.02.2026 | Rice, Oil Seed, Pulse, Maize, Potato | 820 | Yes | Yes
10 | Mizoram | 11 | 11 | 864 | 277 | 32.06% | 150 | 17.36% | 45000 | 13000 | 28.89% | 5000 | 11.11% | 15.12.2025 | 28.02.2026 | Pea, Cabbage, Mustard, Tomato, Bean | 50 | Yes | Yes
11 | Chhattisgarh | 33 | 33 | 20551 | 18959 | 92.25% | 18959 | 92.25% | 25227439 | 18894295 | 74.9% | 18894295 | 74.9% | 01.01.2026 (Approval pending at Administrative Level) | 15,02.2026 (Approval Pending at Administrative Level) | चना,गहू, तबरा/लाख,राई/सरसो,अलसी | 40000 | Yes, on 27.11.2025 | Master Training conducted, Surveyors training will be conducted by Master Trainers in District
12 | Uttar Pradesh | 75 | 75 | 110236 | 95765 | 86.87% | Not Confirmed |  | 76277576 | 54594234 | 71.57% | Not Confirmed |  | 01.01.2026 | 15.02.2026 | Wheat, Mustard, Potato, Pea, Chana, Masoor | Not Confirmed | No, Proposed in 3rd week of Dec | No, Proposed in 3rd week of Dec
13 | Uttarakhand | 13 | 13 | 16691 | 16689 | 99.99% | 6300 | 37.74% | 28383886 | 28383886 | 100% | 10713467 | 37.74% | In Plain districts- 1st January 2026 In Hilly districts- 15th January 2026 | In Plain districts- 15th February 2026 In Hilly districts- 15th May 2026 | Wheat, Barley, Lentil (Masoor), Mustard, Pea | 2300 | Yes | No, in Dec 2nd week
14 | Rajasthan | 41 | 41 | 48909 | 48797 | 99.77% | 48797 | 99.77% | 45459806 | 45238362 | 99.51% | 28051487 | 61.71% | 01.01.2026 | 05.03.2026 | Wheat, Mustard, Chickpea (Gram), Barley, Cumin | 7,870 Pvt Surveyor + 7,714 Govt Patwari | Proposed on 15.12.2025 | Proposed on 24.12.2025
15 | Assam | 35 | 30 | 18407 | 16237 | 88.21% | 12983 | 70.53% | 3909970 | 3909970 | 100% | 3909970 | 100% | 05.01.2026 | 20.02.2026 | Rape & Mustard, Maize, Summer Paddy, Black Gram, Rabi Vegetables | 15453 | No, 19.12.2025 | No. Training shall be conducted by Mastrer Trainer before 31st Dec 2025
16 | Bihar | 38 | 38 | 45536 | 38513 | 84.58% | 30416 | 66.8% | 40000000 | 19400000 | 48.5% | 19400000 | 48.5% | Phase-wise Tentative 24 Dec and later | 31.03.2026 | Wheat, Lentil, Chickpea, Maize, Indian Mustard | 9211 | Yes | No, Proposed by 3rd week of Dec
17 | Madhya Pradesh | 55 | 55 | 56109 | 55431 | 98.79% | 55431 | 98.79% | 47875774 | 47875774 | 100% | 47875774 | 100% | 21.01.2026 | 28.02.2026 |  | 85000 | No,20.01.2026 | No,20.01.2026
18 | Haryana | 22 | 22 | 7103 | 2753 | 38.76% | 2753 | 38.76% | 17846314 | 5487977 | 30.75% | 5487977 | 30.75% | 01.02.2026 | 15.03.2026 | Wheat, Mustard, Gram, Barley, Potato | 5000 | Yes | No, Proposed date 17.12.2025
19 | Andaman & Nicobar | 3 | 3 | 204 | 177 | 86.76% | 177 | 86.76% | 31527 | 25410 | 80.6% | 25410 | 80.6% | 01.02.2026 | 18.03.2026 | 1. Solanaceous crops(Chilli, Brinjal, Tomato etc.) 2. Cucurbitaceous crops(Cucumber,Bottle gourd, Pumpkin, Water Melon etc.) 3. Cole crops(Cabbage, Cauliflower, Knolkhol etc.) 4. Malvaceae crops(Okra) 5. Leafy Vegetable(Spinach, Amaranthus, Poi etc.) | 177 | Yes | No, to be conducted in the 2nd week of Dec
20 | Punjab | 23 | 23 | 13004 | 9371 | 72.06% | 9371 | 72.06% | 22302747 | 13102354 | 58.75% | To be finalized |  | 15.02.2026 (tentative) | 15.04.2026 (tentative) | Wheat, Gram, Barley, Rabi Oil Seeds, Lentil | To be finalized | No, 1st week of Feb (tentative) | No, 1st week of Feb (tentative)
21 | Jammu & Kashmir | 20 | 20 | 6857 | 6014 | 87.71% | 1731 | 25.24% | 6000000 | 5520000 | 92% | 925732 | 15.43% | 15.02.2026 | 15.04.2026 | Oilseed, Wheat, Oats, Vegetables, Field pea | 5000 | Yes | No, Proposed Date 05.01.2026
22 | Goa
23 | Sikkim
24 | Manipur
25 | Arunachal Pradesh
26 | Maharashtra
27 | Karnataka